## Intro (hidden)
| Simple Project Plan Template Excel Free Download | Get our Premium Project Management Templates
Excel Template by analysistabs.com
Info | Excel Project Plan Template for Project Planning and Management
Usage | Enter the Project Details and the Project Timelines in the Required Columns of the Data Table. And the Gantt chart is created automatically based on your data.
About | ProjectPlanTemplate.Net is powered by analysistabs.com (Niruka Tecnologies LLP), provides useful templates for Project Management and Planning. Analysistabs ™ is developing Free and Premium l Project Management Templates. Please do not share this downloaded file. Instead, you can share our free template page link with your colleagues and friends, it helps us to create better tools and more templates.
Visit us
Advanced Templates4
ProjectPlanTemplate.Net
4 Download Now
Niruka Technologies LLP

## Project Plan (1)
Project Name | Data Quality | [7 empty] | Gantt Chart
TOTAL TASKS | 25 |  | Duration | 32 |  | Overall Progress
Completed | 16 |  | Project Start | 2024-08-05
In progress | 3 |  | Project End | 2024-09-05 |  | 66.52%
Not Started | 6
33.48%
Tasks | Responsible | Start Date | End Date | Progress | Status | Duration | Completed | Pending
Personal Information assessment - Mumaris+ | Muhanned | 2024-08-05 | 2024-08-20 | 100% | Completed | 16 | 16 | 0
Communication Information Assessment - Mumaris + | Muhanned | 2024-08-18 | 2024-08-25 | 100% | Completed | 8 | 8 | 0
Profile Information Assessment - Mumaris + | Muhanned | 2024-08-25 | 2024-08-29 | 100% | Completed | 5 | 5 | 0
Personal Information designing DQ Rules in EDW - Mumaris+ | Muhanned | 2024-08-20 | 2024-08-21 | 100% | Completed | 2 | 2 | 0
Communication Information designing DQ Rules in EDW - Mumaris + | Muhanned | 2024-08-25 | 2024-08-26 | 100% | Completed | 2 | 2 | 0
Profile Information designing DQ Rules in EDW - Mumaris + | Muhanned | 2024-08-26 | 2024-09-01 | 100% | Completed | 7 | 7 | 0
Personal Information assessment - Training | Noura | 2024-08-05 | 2024-08-20 | 100% | Completed | 16 | 16 | 0
Communication Information Assessment - Training | Noura | 2024-08-18 | 2024-08-25 | 100% | Completed | 8 | 8 | 0
Personal Information designing DQ Rules in EDW - Training | Noura | 2024-08-25 | 2024-08-29 | 100% | Completed | 5 | 5 | 0
Communication Information designing DQ Rules in EDW - Training | Noura | 2024-08-20 | 2024-08-21 | 100% | Completed | 2 | 2 | 0
All Lookup tables (Listing, Assessment, Development) - Mumaris+ | Muhanned | 2024-09-01 | 2024-09-05 | 20% | In progress | 5 | 1 | 4
All Lookup tables (Listing, Assessment, Development) - Training System | Noura | 2024-08-22 | 2024-08-29 | 33% | In progress | 8 | 3 | 5
Matching System Assessment | Noura | 2024-08-13 | 2024-08-20 | 100% | Completed | 8 | 8 | 0
Matching System designing DQ Rules in EDW | Noura | 2024-08-20 | 2024-08-21 | 100% | Completed | 2 | 2 | 0
Master Data Table 1 (City) - Mumaris+ | Muhanned | 2024-08-18 | 2024-08-22 | 100% | Completed | 5 | 5 | 0
Master Data Table 2 (Medical Field Mapping) - Mumaris+ | Muhanned | 2024-08-18 | 2024-08-22 | 100% | Completed | 5 | 5 | 0
Master Data Table 3 (Specialities) - Mumaris+ | Muhanned | 2024-08-18 | 2024-08-29 | 100% | Completed | 12 | 12 | 0
Master Data Table 4 - Mumaris+ | Muhanned | 2024-08-18 | 2024-08-29 | 0% | Not Started | 12 | 0 | 12
Master Data Table 5 - Mumaris+ | Muhanned | 2024-08-18 | 2024-09-05 | 0% | Not Started | 19 | 0 | 19
Master Data Table 1 Specialities - Training System | Noura | 2024-08-18 | 2024-08-22 | 100% | Completed | 5 | 5 | 0
Master Data Table 2 - Training System | Noura | 2024-08-18 | 2024-08-22 | 0% | Not Started | 5 | 0 | 5
Master Data Table 3 - Training System | Noura | 2024-08-18 | 2024-08-29 | 0% | Not Started | 12 | 0 | 12
Master Data Table 4 - Training System | Noura | 2024-08-18 | 2024-08-29 | 0% | Not Started | 12 | 0 | 12
Master Data Table 5 - Training System | Noura | 2024-08-18 | 2024-09-05 | 0% | Not Started | 19 | 0 | 19
Matching Lookups + Master Data | Noura | 2024-08-18 | 2024-09-05 | 10% | In progress | 19 | 2 | 17
i | This is a free template, you can use this template to plan a small project with 25 tasks. Check our premium templates for multiple projects and more features. Get the unlocked/unprotect version of the templates.
4 View Details

## Noura
Column1 | Start | End | Comments
Personal Information assessment - Training | 2024-08-05 | 2024-08-20 | Done (profiling Sheet, shared report of different names with same ID) | 6-Report to training department
Matching System Assessment | 2024-08-13 | 2024-08-20 | Done (Email Sent By Sarah)
Communication Information designing DQ Rules in EDW - Training | 2024-08-20 | 2024-08-21 | Done (Rules Applied in EDW)
Matching System designing DQ Rules in EDW | 2024-08-20 | 2024-08-21 | Done (Rules Applied in EDW)
Master Data Table 1 - Training System | 2024-08-18 | 2024-08-22 | Done: training Specialities mapping to Mumaris's (200+ Records)
Master Data Table 2 - Training System | 2024-08-18 | 2024-08-22 | Waiting For Abo Omar's List
Communication Information Assessment - Training | 2024-08-18 | 2024-08-25 | Done (profiling Sheet)
Personal Information designing DQ Rules in EDW - Training | 2024-08-25 | 2024-08-29 | Reported To Abo Khalid, and he is working on it (Considered done)
All Lookup tables (Listing, Assessment, Development) - Training System | 2024-08-22 | 2024-08-29 | Listed, and waiting for Abo Omar's List to assesst and develop
Master Data Table 3 - Training System | 2024-08-18 | 2024-08-29 | Waiting For Abo Omar's List
Master Data Table 4 - Training System | 2024-08-18 | 2024-08-29 | Waiting For Abo Omar's List
Master Data Table 5 - Training System | 2024-08-18 | 2024-09-05 | Waiting For Abo Omar's List
Matching Lokups + Master Data | 2024-08-18 | 2024-09-05 | Mapped Matching specialities with Mumaris+, still waiting for abo Omars list to proceed.

## Muhanned
Column1 | Start | End | Comments
Personal Information assessment - Mumaris+ | 2024-08-05 | 2024-08-20 | Done
Personal Information designing DQ Rules in EDW - Mumaris+ | 2024-08-20 | 2024-08-21 | Done
Master Data Table 1 - Mumaris+ | 2024-08-18 | 2024-08-22 | Done(City)
Master Data Table 2 - Mumaris+ | 2024-08-18 | 2024-08-22 | Done(Medical_Field)
Communication Information Assessment - Mumaris + | 2024-08-18 | 2024-08-25 | Done
Communication Information designing DQ Rules in EDW - Mumaris + | 2024-08-25 | 2024-08-26 | Done
Profile Information Assessment - Mumaris + | 2024-08-25 | 2024-08-29 | Done
Master Data Table 3 - Mumaris+ | 2024-08-18 | 2024-08-29 | Done(Specialty)
Master Data Table 4 - Mumaris+ | 2024-08-18 | 2024-08-29 | Waiting (From Mohammed Ahmed )
Profile Information designing DQ Rules in EDW - Mumaris + | 2024-08-26 | 2024-09-01 | Done
All Lookup tables (Listing, Assessment, Development) - Mumaris+ | 2024-09-01 | 2024-09-05 | Listing Done, waiting from Mohammed Ahmed
Master Data Table 5 - Mumaris+ | 2024-08-18 | 2024-09-05 | Waiting (From Mohammed Ahmed )

## M. Ahmed
Column1 | Column2 | Start | End | Comments
Master Data Table 2 - Training System | Noura | 2024-08-18 | 2024-08-22 | Waiting For Abo Omar's List
Master Data Table 3 - Training System | Noura | 2024-08-18 | 2024-08-29 | Waiting For Abo Omar's List
Master Data Table 4 - Training System | Noura | 2024-08-18 | 2024-08-29 | Waiting For Abo Omar's List
Master Data Table 5 - Training System | Noura | 2024-08-18 | 2024-09-05 | Waiting For Abo Omar's List
All Lookup tables (Listing, Assessment, Development) - Training System | Noura | 2024-08-22 | 2024-08-29 | Listed, and waiting for Abo Omar's List to assesst and develop
Master Data Table 4 - Mumaris+ | Muhanned | 2024-08-18 | 2024-08-29 | Waiting (From Mohammed Ahmed )
Master Data Table 5 - Mumaris+ | Muhanned | 2024-08-18 | 2024-09-05 | Waiting (From Mohammed Ahmed )

## NDMO
Column1 | Start | End | Comments
Data Quality Rules Development - Mumaris+ (phase 1) | 2024-08-18 | 2024-08-29 | Done
Data Quality Monitoring - Mumaris+ (phase 1) | 2024-09-01 | 2024-09-12 | we have a dashboard that reflect the update to monitoring the issues correction
Data Quality Issues Resolution - Mumaris+ (phase 1) | 2024-08-05 | 2024-08-15 | Data Profiling ()
Data Quality Service Level Agreements - Mumaris+ (phase 1) | 2024-08-18 | 2024-08-29 | Waiting from hanin
Data Quality Tools - Mumaris+ (phase 1) | 2024-09-01 | 2024-09-12 | We are automate the profiling and we can add the role to automate the role test -
Data Quality Trends - Mumaris+ (phase 1) | 2024-08-05 | 2024-08-27 | Done Need more awareness Done
Data Quality Issues Resolution - Mumaris+ (phase 1) | 2024-08-27 | 2024-09-05 | Done
Data Quality Checkpoints - Mumaris+ (phase 1) | 2024-08-05 | 2024-08-27 | Done(Specialty)
Data Quality Support (Process+Tool) - Mumaris+ (phase 1) | 2024-08-27 | 2024-09-05 | Working to create a clear workflow based on the department and still don't have tools for that
Data Quality Metadata - Mumaris+ (phase 1) | 2024-04-02 | 2024-04-15 | Done

## Project Plan (2)
Project Name | NDMO - Data Quality Compliance | [7 empty] | Gantt Chart
TOTAL TASKS | 21 |  | Duration | 167 |  | Overall Progress
Completed | 0 |  | Project Start | 2024-04-02
In progress | 2 |  | Project End | 2024-09-15 |  | 4.524%
Not Started | 19
95.48%
Tasks | Responsible | Start Date | End Date | Progress | Status | Duration | Completed | Pending
Data Quality Framework | Mohammed Alqahtani | 2024-08-05 | 2024-09-15 | 25% | In progress | 42 | 11 | 31
Data Quality Rules Development - Mumaris+ (phase 1) | Muhanned | 2024-08-18 | 2024-08-29 | 70% | In progress | 12 | 8 | 4
Data Quality Monitoring - Mumaris+ (phase 1) | Muhanned | 2024-09-01 | 2024-09-12 | 0% | Not Started | 12 | 0 | 12
Data Quality Issues Resolution - Mumaris+ (phase 1) | Muhanned | 2024-08-05 | 2024-08-15 | 0% | Not Started | 11 | 0 | 11
Data Quality Service Level Agreements - Mumaris+ (phase 1) | Muhanned | 2024-08-18 | 2024-08-29 | 0% | Not Started | 12 | 0 | 12
Data Quality Tools - Mumaris+ (phase 1) | Muhanned | 2024-09-01 | 2024-09-12 | 0% | Not Started | 12 | 0 | 12
Data Quality Trends - Mumaris+ (phase 1) | Muhanned | 2024-08-05 | 2024-08-27 | 0% | Not Started | 23 | 0 | 23
Data Quality Issues Resolution - Mumaris+ (phase 1) | Muhanned | 2024-08-27 | 2024-09-05 | 0% | Not Started | 10 | 0 | 10
Data Quality Checkpoints - Mumaris+ (phase 1) | Muhanned | 2024-08-05 | 2024-08-27 | 0% | Not Started | 23 | 0 | 23
Data Quality Support (Process+Tool) - Mumaris+ (phase 1) | Muhanned | 2024-08-27 | 2024-09-05 | 0% | Not Started | 10 | 0 | 10
Data Quality Metadata - Mumaris+ (phase 1) | Muhanned | 2024-04-02 | 2024-04-15 | 0% | Not Started | 14 | 0 | 14
Data Quality Rules Development - Training System (phase 1) | Nourah | 2024-04-02 | 2024-04-15 | 0% | Not Started | 14 | 0 | 14
Data Quality Monitoring - Training System (phase 1) | Nourah | 2024-04-02 | 2024-04-15 | 0% | Not Started | 14 | 0 | 14
Data Quality Issues Resolution -Training System (phase 1) | Nourah | 2024-04-02 | 2024-04-15 | 0% | Not Started | 14 | 0 | 14
Data Quality Service Level Agreements - Training System (phase 1) | Nourah | 2024-04-02 | 2024-04-15 | 0% | Not Started | 14 | 0 | 14
Data Quality Tools - Training System (phase 1) | Nourah | 2024-04-02 | 2024-04-15 | 0% | Not Started | 14 | 0 | 14
Data Quality Trends - Training System (phase 1) | Nourah | 2024-04-02 | 2024-04-15 | 0% | Not Started | 14 | 0 | 14
Data Quality Issues Resolution - Training System (phase 1) | Nourah | 2024-04-02 | 2024-04-15 | 0% | Not Started | 14 | 0 | 14
Data Quality Checkpoints - Training System (phase 1) | Nourah | 2024-04-02 | 2024-04-15 | 0% | Not Started | 14 | 0 | 14
Data Quality Support (Process+Tool) - Training System (phase 1) | Nourah | 2024-04-02 | 2024-04-15 | 0% | Not Started | 14 | 0 | 14
Data Quality Metadata - Training System (phase 1) | Nourah | 2024-04-02 | 2024-04-15 | 0% | Not Started | 14 | 0 | 14
[6 empty] | #N/A | #N/A | #N/A
[6 empty] | #N/A | #N/A | #N/A
[6 empty] | #N/A | #N/A | #N/A
[6 empty] | #N/A | #N/A | #N/A
i | This is a free template, you can use this template to plan a small project with 25 tasks. Check our premium templates for multiple projects and more features. Get the unlocked/unprotect version of the templates.
4 View Details

## Task Description
Project | Project Plan Sheet | Task | Description
DQ NDMO Compliance | 2 | Data Quality Rules Development | Read Control specification P. 46
| 2 | Data Quality Monitoring | Read Control specification P. 47
| 2 | Data Quality Issues Resolution | Read Control specification P. 47
| 2 | Data Quality Service Level Agreements | Read Control specification P. 48
| 2 | Data Quality Tools | Read Control specification P. 48
| 2 | Data Quality Trends | Read Control specification P. 49
| 2 | Data Quality Issues Resolution | Read Control specification P. 49
| 2 | Data Quality Checkpoints | Read Control specification P. 51
| 2 | Data Quality Support (Process+Tool) | Read Control specification P. 51
| 2 | Data Quality Metadata | Read Control specification P. 51
Data Quality | 1 | Personal Information assessment - Mumaris+ | Exploring Issuses + Profiling it
| 1 | Communication Information Assessment - Mumaris + | Exploring Issuses + Profiling it
| 1 | Profile Information Assessment - Mumaris + | Exploring Issuses + Profiling it
| 1 | Personal Information designing DQ Rules in EDW - Mumaris+ | Creating DQ rules for found issues + adding it to DQ rules in EDW
| 1 | Communication Information designing DQ Rules in EDW - Mumaris + | Creating DQ rules for found issues + adding it to DQ rules in EDW
| 1 | Profile Information designing DQ Rules in EDW - Mumaris + | Creating DQ rules for found issues + adding it to DQ rules in EDW
| 1 | Personal Information assessment - Training | Exploring Issuses + Profiling it
| 1 | Communication Information Assessment - Training | Exploring Issuses + Profiling it
| 1 | Personal Information designing DQ Rules in EDW - Training | Exploring Issuses + Profiling it
| 1 | Communication Information designing DQ Rules in EDW - Training | Creating DQ rules for found issues + adding it to DQ rules in EDW
| 1 | All Lookup tables (Listing, Assessment, Development) - Mumaris+ | Review, assess, develop (if needed), and report All lookups
| 1 | All Lookup tables (Listing, Assessment, Development) - Training System | Review, assess, develop (if needed), and report All lookups
| 1 | Matching System Assessment | Exploring Issuses + Profiling it
| 1 | Matching System designing DQ Rules in EDW | Creating DQ rules for found issues + adding it to DQ rules in EDW
| 1 | Master Data Table 1 - Mumaris+ | Discuss it with Mohammed Ahmed to choose 1 Master data table, name it, then develop it
| 1 | Master Data Table 2 - Mumaris+ | Discuss it with Mohammed Ahmed to choose 1 Master data table, name it, then develop it
| 1 | Master Data Table 3 - Mumaris+ | Discuss it with Mohammed Ahmed to choose 1 Master data table, name it, then develop it
| 1 | Master Data Table 4 - Mumaris+ | Discuss it with Mohammed Ahmed to choose 1 Master data table, name it, then develop it
| 1 | Master Data Table 5 - Mumaris+ | Discuss it with Mohammed Ahmed to choose 1 Master data table, name it, then develop it
| 1 | Master Data Table 1 - Training System | Discuss it with Mohammed Ahmed to choose 1 Master data table, name it, then develop it
| 1 | Master Data Table 2 - Training System | Discuss it with Mohammed Ahmed to choose 1 Master data table, name it, then develop it
| 1 | Master Data Table 3 - Training System | Discuss it with Mohammed Ahmed to choose 1 Master data table, name it, then develop it
| 1 | Master Data Table 4 - Training System | Discuss it with Mohammed Ahmed to choose 1 Master data table, name it, then develop it
| 1 | Master Data Table 5 - Training System | Discuss it with Mohammed Ahmed to choose 1 Master data table, name it, then develop it
| 1 | Matching Lokups + Master Data | Find all Master data and lookups tables, assess and then develop it if needed

## TRD Tables
# | Table Name | LU/MD/Data | System | Communication/Personal/Both
1 | trd_tbl_AccountTypes | LU | TR
2 | trd_tbl_All_Exams | Data | TR | Personal
3 | trd_tbl_All_Exams_Log | Data | TR | Personal
4 | trd_tbl_BoardType | LU | TR
5 | trd_tbl_CenterType | LU | TR
6 | trd_tbl_ChangesTypes | LU | TR
7 | trd_tbl_CityName | MD | TR
8 | trd_tbl_CitySector | LU | TR
9 | trd_tbl_Duration | LU | TR
10 | trd_tbl_eL_Invoices | Data | TR | Personal
11 | trd_tbl_eL_Invoices_Log | Data | TR
12 | trd_tbl_eL_Payment_Mls_Invoices_logs | Data | TR
13 | trd_tbl_eL_RequestStatuses | LU | TR
14 | trd_tbl_el_traineesInfo | Data | TR | Personal
15 | trd_tbl_ExamType | LU | TR
16 | trd_tbl_FinancialRequests | Data | TR
17 | trd_tbl_FinancialRequestsTypes | LU | TR
18 | trd_tbl_GenderName | LU | TR
19 | trd_tbl_Invoices | Data | TR | Personal
20 | trd_tbl_Invoices_Log | Data | TR | Personal
21 | trd_tbl_InvoiceStatus | LU | TR
22 | trd_tbl_InvoiceType | LU | TR
23 | trd_tbl_LevelName | LU | TR
24 | trd_tbl_LevelSatus | LU | TR
25 | trd_tbl_MasterTrainingCenters | MD | TR
26 | trd_tbl_NationalityName | MD | TR
27 | trd_tbl_PaymentMethods | LU | TR
28 | trd_tbl_ProgramLevelStatus | LU | TR
29 | trd_tbl_PromotionCriteriaCategories | LU | TR
30 | trd_tbl_Promotions | Data | TR
31 | trd_tbl_PromotionStatus | LU | TR
32 | trd_tbl_PromotionTypes | LU | TR
33 | trd_tbl_RefundType | LU | TR
34 | trd_tbl_Region | MD | TR
35 | trd_tbl_ResultTypes | LU | TR
36 | trd_tbl_SCFHS_Departments | LU | TR
37 | trd_tbl_Speciality | MD | TR
38 | trd_tbl_SpecialityCategory | LU | TR
39 | trd_tbl_SpecialityType | LU | TR
40 | trd_tbl_TraineesLevel | Data | TR
41 | trd_tbl_TraineesProgram | Data | TR
42 | trd_tbl_TraineesProgramLogs | Data | TR
43 | trd_tbl_TraineesRecords | Data | TR | Both
44 | trd_tbl_TrainingBoxes | MD | TR
45 | trd_tbl_TrainingCenter | MD | TR
46 | trd_tbl_TrainingCompletion | Data | TR | Personal
47 | trd_tbl_University_code | MD | TR
48 | trd_tbl_WorksName | MD | TR
49 | citybase | MD | M+
50 | scfhs_classificationBase | MD | M+
51 | scfhs_countryBase | MD | M+
52 | Exams | MD | M+
53 | Medical_Field | MD | M+
54 | Specialities | MD | M+
55 | University | MD | M+
56 | University_Branch | MD | M+
57 | Work_Place | MD | M+
| citybase |  | Mustamir
| Classification Rank |  | Mustamir
| Countries |  | Mustamir
| Medical_Field |  | Mustamir
| Specialities |  | Mustamir
| Specialities |  | Muetamed
| Training Center |  | Muetamed
| Training Sector |  | Muetamed

## Profiling
ID | System | Table | Column | Problem | Possible Cause | Descr | Query | Class | # | Example | Column1
1 | Mumaris+ | ContactBase | FirstName | Incorrect First name |  | The first name have only 2 digits or less | select FirstName,scfhs_ApplicantId from ContactBase a where len(a.FirstName) <3 and scfhs_RegistrationExpirydate > getdate() | Personal Information | 560
2 | Mumaris+ | ContactBase | LastName | Incorrect Lastname |  | The Last name have only 2 digits or less | select LastName,scfhs_ApplicantId from ContactBase a where len(a.LastName) <3 and scfhs_RegistrationExpirydate > getdate() | Personal Information | 780
3 | Mumaris+ | ContactBase | BirthDate | Birthdate less than 18 |  | The birthdate is less than 18 Years | select BirthDate,datediff(Year,BirthDate,getdate()) from ContactBase a where datediff(Year,BirthDate,getdate()) < 18 and scfhs_RegistrationExpirydate > getdate() | Personal Information | 101
4 | Mumaris+ | ContactBase | LastName | Incorrect Lastname |  | The last name have 20 digits or less | select LastName,scfhs_ApplicantId from ContactBase a where len(a.LastName) >20 and scfhs_RegistrationExpirydate > getdate() | Personal Information | 288
5 | Mumaris+ | ContactBase | FirstName | Incorrect First name |  | The First name have 20 digits or less | select FirstName,scfhs_ApplicantId from ContactBase a where len(a.FirstName) >20 and scfhs_RegistrationExpirydate > getdate() | Personal Information | 60
6 | Mumaris+ | ContactBase | scfhs_birthcountries | The birth country is null |  | We have a list of valid Practitioners don't have birth country | select * from ContactBase a left join scfhs_country b on a.scfhs_birthcountries = b.scfhs_countryId where scfhs_RegistrationExpirydate > getdate() and b.scfhs_CountryNameInArabic is null | Personal Information | 274
7 | Mumaris+ | ContactBase | scfhs_countryofstudy | The study country is null |  | We have a list of valid Practitioners don't have study country | select * from ContactBase a left join scfhs_countryBase b on a.scfhs_countryofstudy = b.scfhs_countryId where scfhs_RegistrationExpirydate > getdate() and b.scfhs_CountryNameInArabic is null | Personal Information | 310728
8 | Mumaris+ | ContactBase | scfhs_PassportNumber | Incorrect passport id |  | We have a list of valid Practitioners have incorrect passport number | select * from ContactBase with(nolock) where scfhs_RegistrationExpirydate > getdate() and scfhs_ispassport = 1 and( len(scfhs_PassportNumber) <7 or len(scfhs_PassportNumber) >11 ) | Personal Information | 28
9 | Training | trd_tbl_TraineesRecords | dtDateBirthGer | birthdate is null |  | records with null gergorian date of birth | SELECT * FROM trd_tbl_TraineesRecords WHERE dtDateBirthGer IS NULL; | Personal Information | 14595
10 | Mumaris+ | ContactBase | Ispassport | Registeration trough passport and saudi |  | we have a list of valid Practitioners are registered through passport with saudi nationality | select scfhs_nationalities from ContactBase a where scfhs_RegistrationExpirydate > getdate() and scfhs_nationalities = 'BD02F5A9-5EF9-E811-B80F-005056AD2FD8' and scfhs_ispassport = 1 | Personal Information | 182
11 | Training | trd_tbl_TraineesRecords | dtDateBirthGer | gergorian date before 1930 |  |  | select * from trd_tbl_TraineesRecords where dtDateBirthGer < '1930-01-01' | Personal Information | 13045
12 | Training | trd_tbl_TraineesRecords | dtDateBirthHijri | birthdate is null |  | saudis with null hijri birthdate | SELECT * FROM trd_tbl_TraineesRecords WHERE dtDateBirthHijri IS NULL and intNationality=1; | Personal Information | 28586
13 | Training | trd_tbl_TraineesRecords | intGender | gender is 3 |  |  | SELECT x.* FROM [DDO-SCFHS-ODS].dbo.trd_tbl_TraineesRecords x WHERE intGender IN (3) | Personal Information | 1
14 | Training | trd_tbl_TraineesRecords | ClassificationNumber | classification number is null |  |  | select * from trd_tbl_TraineesRecords where ClassificationNumber is null | Business Information | 14032
15 | Mumaris+ | ContactBase | Registration_issued_Date,Registration_Expiry_Date | The registration expiry Date is Greater Than Issued Date |  | We have 207 Practitioners that is the Expiry date greater than issued date | select scfhs_ApplicantId,FirstName from ContactBase a left join scfhs_countryBase b on a.scfhs_countryofresidence = b.scfhs_countryId where --scfhs_RegistrationExpirydate > getdate() and scfhs_RegistrationExpirydate < scfhs_registrationissuedate | Profile Information | 207
16 | Mumaris+ | ContactBase | Duration | the Duration for the registration is incorrect |  | we have a list of Valid practitioners that have more than 2 Years as a duration for registration | select scfhs_ApplicantId from ContactBase a where scfhs_RegistrationExpirydate > getdate() and datediff(year,scfhs_registrationissuedate,scfhs_RegistrationExpirydate) > 2 | Profile Information | 106
17 | Mumaris+ | IncidentBase | Medical field and speciality | Incorrect medical field |  | We have a list fo practitioners don't have a correct medical field | select a.scfhs_MedicalProfessionalField,b.GroupNameAR,scfhs_Speciality,c.scfhs_SpecialtyNameInArabic,count(*) from [dbo].[IncidentBase] a with (Nolock) left join medicalprofessionalfield b with (Nolock) on a.scfhs_MedicalProfessionalField=b.GroupId left join scfhs_specialtyBase c with (Nolock) on a.scfhs_Speciality=c.scfhs_specialtyId where scfhs_RegistrationExpirydate > getdate() group by a.scfhs_MedicalProfessionalField,scfhs_Speciality,b.GroupNameAR,c.scfhs_SpecialtyNameInArabic order by scfhs_SpecialtyNameInArabic | Profile Information |  | 23597985 23597985 24656112 24656112 07AN0017237 06JN27479 12RN0049013 12RN0005294 04KN1072 07KN9723 05RN4892 20233536
18 | Training | trd_tbl_TraineesRecords | dtDateBirthGer | birthdate less than 18 |  |  | select * from trd_tbl_TraineesRecords where dtDateBirthGer > '2006-01-01' | Personal Information | 107
19 | Training | trd_tbl_TraineesRecords | dtDateBirthHijri | hijri birthdate after 1428H |  | mostrly format issue | select * from trd_tbl_TraineesRecords where dtDateBirthHijri > '1428-01-01' | Personal Information | 9440 | format issue: 2008075514331 Accuracy issue: 2008050314573
20 | Training | trd_tbl_TraineesRecords | dtDateBirthHijri | hijri birthdate before 1350H |  | mostrly format issue | select * from trd_tbl_TraineesRecords where dtDateBirthHijri < '1350-01-01' | Personal Information | 7452 | format issue: 2011070219944 Accuracy issue: 2012020222833
21 | Training | trd_tbl_TraineesRecords | strNationalIqamID | Null IDs |  |  | select * from trd_tbl_TraineesRecords where strNationalIqamID is null | Personal Information | 755
22 | Training | trd_tbl_TraineesRecords | strMobileNumber | Null Mobile Numbers |  |  | select * from trd_tbl_TraineesRecords where strMobileNumber is null | Communication Number | 3757
23 | Training | trd_tbl_TraineesRecords | strEmail | Nul Emails |  |  | select * from trd_tbl_TraineesRecords where strEmail is null | Communication Number | 3523
24 | Training | trd_tbl_TraineesRecords | strMobileNumber | digit count |  | digitd count doesnt suffice saudi phone number | select * from trd_tbl_TraineesRecords where LEN(strMobileNumber) not IN (12, 10, 9) | Communication Number | 817
25 | Training | trd_tbl_TraineesRecords | strMobileNumber | wrong format |  | wrong format within suffice saudi number digit count | select * from trd_tbl_TraineesRecords where LEN(strMobileNumber) not IN (12, 10, 9) or(LEN(strMobileNumber) IN (10) and strMobileNumber not like '05%' ) or(LEN(strMobileNumber) IN (12) and strMobileNumber not like '9665%' ) or (LEN(strMobileNumber) IN (9) and strMobileNumber not like '5%' ) | Communication Number | 270
26 | training | trd_tbl_TraineesRecords | strEmail | wrong email |  | no '@' symbol | select * from trd_tbl_TraineesRecords where strEmail not like '%@%' | Communication Number | 121
27 | training | trd_tbl_TraineesRecords | strEmail | wrong email |  | not having at least two letters after . | select * from trd_tbl_TraineesRecords where strEmail not like ('%@%.__%') | Communication Number | 387
28 | training | trd_tbl_TraineesRecords | strEmail | wrong email |  | empty string | select * from trd_tbl_TraineesRecords where strEmail like '' | communication Number | 81
29 | training | trd_tbl_TraineesRecords | strNationalIqamID | incorrect saudi id |  | wrong length and wrong format | select * from trd_tbl_TraineesRecords where len(strNationalIqamID) not in (10) and strNationalIqamID not like '1%' and intNationality=1 | Personal Information | 14
30 | training | trd_tbl_TraineesRecords | strNationalIqamID | incorrect iqama number |  | wrong length and wrong format | select * from trd_tbl_TraineesRecords where len(strNationalIqamID) not in (10) and strNationalIqamID like '2%' and intNationality=1 | Personal Information | 7
31 | training | trd_tbl_TraineesRecords | strNationalIqamID | incorrect saudi id |  | correct length with wromg format | select * from trd_tbl_TraineesRecords where len(strNationalIqamID) in (10) and strNationalIqamID not like '1%' and intNationality =1 | Personal Information | 92
32 | training | trd_tbl_TraineesRecords | strNationalIqamID | incorrect |  | wrong iqama format | select * from trd_tbl_TraineesRecords where len(strNationalIqamID) in (10) and strNationalIqamID like '1%' and intNationality !=1 | Personal Information | 24
33 | training | trd_tbl_TraineesRecords | strNationalIqamID | incorrect |  | incorrect number of digits | select * from trd_tbl_TraineesRecords where len(strNationalIqamID) not in (10) | Personal Information | 1048
34 | training | trd_tbl_TraineesRecords | strSecondArabicName | short second name |  | secrond name for saudi trainees less than 2 digits | select * from trd_tbl_TraineesRecords where intNationality=1 and len(strSecondArabicName)<2 | Personal Information | 14
35 | Mumaris+ | IncidentBase | scfhs_MedicalProfessionalField, scfhs_Speciality | same Speciality with different Medical Field |  | we have a list of practitioners that have a same speciaity with different medical field | select a.scfhs_MedicalProfessionalField,b.GroupNameAR,scfhs_Speciality,c.scfhs_SpecialtyNameInArabic,count(*) from [dbo].[IncidentBase] a with (Nolock) left join medicalprofessionalfield b with (Nolock) on a.scfhs_MedicalProfessionalField=b.GroupId left join scfhs_specialtyBase c with (Nolock) on a.scfhs_Speciality=c.scfhs_specialtyId where scfhs_RegistrationExpirydate > getdate() group by a.scfhs_MedicalProfessionalField,scfhs_Speciality,b.GroupNameAR,c.scfhs_SpecialtyNameInArabic order by scfhs_SpecialtyNameInArabic | Profile Information |  |  | select a.scfhs_MedicalProfessionalField,l.AttributeName,scfhs_Speciality,c.scfhs_SpecialtyNameInArabic,count(*),l.Value from [dbo].[IncidentBase] a with (Nolock) --left join medicalprofessionalfield b with (Nolock) on a.scfhs_MedicalProfessionalField=b.GroupId left join scfhs_specialtyBase c with (Nolock) on a.scfhs_Speciality=c.scfhs_specialtyId left join StringMapBase L on a.scfhs_MedicalProfessionalField=l.AttributeValue and l.AttributeName='scfhs_professionalmedicalfield' and LangId=1025 where scfhs_RegistrationExpirydate > getdate() group by a.scfhs_MedicalProfessionalField,scfhs_Speciality,l.AttributeName,c.scfhs_SpecialtyNameInArabic,l.Value order by scfhs_SpecialtyNameInArabic
36 | Training and Mumaris | trd_tbl_TraineesRecords / ContactBase | intRegistrationNumber / scfhs_trainingregid | Map Trainees intRegistrationNumber correctly with scfhs_trainingregid cuz the later is unreliable |  |  |  | Business Information
37 | Training | trd_tbl_Speciality | intSpecialityType / strSpecialityType | the columns arent mapped correctly |  |  |  | Business Information
38 | Training
39 | Training
40 | Training
41 | Training
42 | Training
43 | Training
44 | Training
45 | Training
46 | Mumaris+ | Contact_base | MobilePhone | The same mobile number has more than 1 active account |  |  | select a.scfhs_ApplicantId,a.MobilePhone from ( select ROW_NUMBER() over (partition by MobilePhone order by createdon ) rn,* from ContactBase with (Nolock) )a where rn>1 and MobilePhone is not null and a.scfhs_profilestatus in (776070000) and scfhs_RegistrationExpirydate > getdate() order by a.MobilePhone | Communication Information | 6205 | 502833721
47 | Mumaris+ | Contact_base | - | Document type is not defined | The document selection is not mandetory |  | select scfhs_ApplicantId from ContactBase with(nolock) where scfhs_RegistrationExpirydate > getdate() and scfhs_isnic <> 1 and scfhs_ispassport <> 1 and scfhs_isgcc <> 1 and scfhs_IsAjeer <> 1
48 | Mumaris+ | Contact_base | scfhs_PassportNumber | Allow null and no restriction |  |  | select scfhs_PassportID,scfhs_PassportNumber from ContactBase a where scfhs_RegistrationExpirydate > getdate() and scfhs_PassportNumber not like N'%[0-9]%' and scfhs_ispassport = 1
50 | Mumaris+ | Contact_base | scfhs_nationalities | Allow All nationality selection in GCC Choise |  |  | select scfhs_ApplicantId,* from ContactBase a where scfhs_RegistrationExpirydate > getdate() and scfhs_nationalities <> '6D03F5A9-5EF9-E811-B80F-005056AD2FD8' and scfhs_nationalities <>'5603F5A9-5EF9-E811-B80F-005056AD2FD8' and scfhs_nationalities <> 'EC02F5A9-5EF9-E811-B80F-005056AD2FD8'and scfhs_nationalities <>'0703F5A9-5EF9-E811-B80F-005056AD2FD8' and scfhs_nationalities <> '0003F5A9-5EF9-E811-B80F-005056AD2FD8' and scfhs_isgcc = 1
51 | Mumaris+ | Contact_base
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114

## License (hidden)
License Terms
4 | Analysistabs™ License Agreement
This Template/Excel File and sample data is created by Analysistabs™ (Niruka Technologies LLP)
4 | Licensed Product: Single User License to Analysistabs™ Project Plan Template
4 | Single User License: Allows 1 (Personal Use Only).
4 | You are Allowed
4 | Individual users are permitted to use this template for their personal use only
4 | You can share the template page link:(https://analysistabs.com/project/management/)
4 | You can make copies for your own use
4 | You are NOT Allowed
4 | Reproducing of this template is not permitted for reselling, rebranding, team usage, company usage, training and any other business purpose.
4 | You are not allowed to share this template, or the screenshots/ images produced using this template with sample data provided in the template.
4 | You are not allowed to share our template via Emails, Shared drives, Common Folders, Websites, and Social media
4 | You must not remove our copyright notices and Licence sheets from the template
4 | The templates (.xlsx,.xlsm, .docx, .pptx) files should not be shared with others. Instead, you can share following web page link of this template.
Link: | https://analysistabs.com/project/management/
Niruka Technologies LLP